## Sheet1
[5 empty] | Project Name | HR Admin
Module Name
[5 empty] | Document Type | Bug report
[5 empty] | Technology | PHP
[5 empty] | Author | Shweta Soner
[5 empty] | Start Date | 2017-12-25
End Date
Retesting date
S.no | Bug_ID | Window | Element | Scenario | Expected Result | Actual Result | Status | Developer status | Retestng date | Date | Image no
1 | Bug_01 | Employee | Add employee | To add employee | It should show in list | added employee name is not showing | Fail
2 | Bug_02 | employee | Add employee | To enter numeric values in name field | It shoud be show error message | it is accepting numeric values in name fields | Fail
3 | Bug_03 | employee | Add employee | To enter alpha values in name field | it should be show error message | it is accepting alpha values in name fields | Fail
4 | Bug_04 | Attendae | Clock out time | without punch out to check clock out time(in view section) | it shouldn't show punch out time ,without punch out | it is showing check at every new account | Fail
5 | Bug_05 | Empoyee | Trasfer | To add transfer and edit them | It shoud be edit | Edit functionality is not working | Fail
6 | Bug_06 | Empoyee | Add termination | To add termination | It should be add | it is not saving all data | Fail
7 | Bug_07 | Add company | Add contact | To check contact field | There number increaing dropdown is not required | It is showing at contact side | Fail
9 | Bug_09 | Attandace | Early leaving | To check earling leaving time | it should be show correct (niti id/4 hour ) | It is showing 9 hour 7 mit .please correct it. | Fail